## EN
Update | Date | T2S Release Schedule | CBF / T2S Business Day (CET) | Revision | Revised Time (CEST) | Description of Event / Process of regular T2S Operational Day | CBF Comment
| Monday, 20 June 2022 |  |  |  |  | Operational News #1 SET-GO: Pre-Migration - Maintenance of static data account | Temporary stop of the maintenance of static data requested for the preparation of the migration of non-cleared Stock Exchange trades (non-CCP SE trades).
| Monday, 27 June 2022 |  |  |  |  | Operational News #2 CBF: July Release Weekend Schedule - Final update | Last update of the "Indicative Timeline" in preparation of the deployment weekend.
| Friday, 1 July 2022 |  |  |  | 9:00 | Operational News #3 SET-GO: Pre-Migration – Cancellation request of outdated pending LION instructions | Supporting the SET-GO migration activities, customers are invited to cancel no longer necessary LION instructions latest by 1 July 2022, at 15:45.
| Friday, 1 July 2022 |  |  |  | 16:00 | Operational News #4 SET-GO: Migration – Automated cancellation of pending LION instructions | CASCADE HOST transactions (TRAN) KVLA and KVLS will be blocked for instruction maintenance. Only transaction KVLI remains open as read-only.
| Friday, 1 July 2022 | until 18:45 |  |  |  | T2S Operational Day and CBF T2S Business Day will be executed based on the regular schedules
| Friday, 1 July 2022 | 18:45 |  | è | Saturday, 2 July 2022, 15:10 | T2S – Continue with Operating Day | On T2S, the new business day will start as soon as the deployment activities have been completed.
| Friday, 1 July 2022 |  | 19:00 | ü |  | CBF – Start of Day | CBF will change to value day, Monday, 4 July 2022, according to the regular schedule.
| Friday, 1 July 2022 |  | 19:00 | û |  | LION – Start STD settlement | STD processing will be deactivated with the start of the migration. Pending instructions in CSC and NCSC-T securities will be migrated this weekend. They will be processed "OTC like" in T2S / CASCADE in the future.
| Friday, 1 July 2022 |  | 19:00 | ü |  | CBF Print Report: (settlement list)
| Friday, 1 July 2022 |  | 19:15 | è | Sunday, 3 July 2022, 06:00 | LION – Start LION Online
| Friday, 1 July 2022 |  |  |  | 19:30 | Operational News #5 CBF: Completion end of day processing | The CBF business day 1 July 2022 to be closed and the End of Day (EoD) reporting will be prepared according to this timeline.
| Friday, 1 July 2022 |  | 19:30 | è | Friday, 1 July 2022, 23:00 | KADI Reporting: MT564 – Notification MT568 – Narrative | CBF processing for corporate actions (KADI) will continue to be conducted according to the general procedures. This Friday, KADI reporting will be delivered later. This measure will ensure that all information coming from the KADI processing will be transmitted on the same day.
| Friday, 1 July 2022 |  | 19:30 | è | Sunday, 3 July 2022, 08:00 | KADI Reporting: MT566 – Confirmations | The corporate action confirmations (MT566) will be available Sunday, 3 July 2022, at 08:00.
| Friday, 1 July 2022 |  | 20:00 | ü |  | Clearstream Online Functionality | The CASCADE Online functionality (HOST / PC) and the Xact Web Portal will not be fully available during the implementation phase. A separate time frame to access CASCADE Online Functonalities (HOST / PC) will be available on Sunday, 3 July 2022, between 06:30 and 11:00.
| Friday, 1 July 2022 |  | 19:45 | è | Sunday, 3 July 2022, 06:00 | CBF's real-time interface to T2S | Clearstream will close its connectivity interface (T2S-I) to T2S while executing deployment activities. However, CBF’s automated connectivity channels will be open for the customers. That is, any instruction provided to CBF for T2S will be queued until the implementation phase in CBF is finalised Sunday, 3 July 2022, at around 06:00. This means, that any instruction successfully transmitted will be on hold on connectivity layer. Afterwards the transmission window has to be closed for T2S Release 6.0 deployment activities.
| Friday, 1 July 2022 |  |  |  | 20:00 | Operational News #6 T2S: End of processing of incoming messages | Based on the T2S Deployment Playbook, the CSDs will be informed by T2S that incoming messages through the existing connectivity channel will not be accepted anymore. Customers acting in DCP mode are requested to monitor the message flow with T2S from this time on. Earliest from 22:00, messages received through ESMIG will be queued until the end of the deployment and then processed.
| Friday, 1 July 2022 |  |  |  | 20:30 | Operational News #7 T2S: Green Light for software deployment | T2S will give "Green Light" for the deployment activities in close cooperation with the T2S Settlement Managers.
| Friday, 1 July 2022 | 20:00 |  | è | Saturday, 2 July 2022, 16:25 | T2S – Start Night-time Settlement (NTS), Start First NTS Cycle | T2S will close the transfer queue for liquidity transfer on Friday, 1 July 2022 at around 18:50. The liquidity transfers initiated by customers in TARGET2 on will be related by T2S on Saturday, 2 July 2022, at around 15:25 so that the credit to the DCAs can be executed.
| Friday, 1 July 2022 |  | 20:30 | ü |  | CASCADE Reporting: MT535 – Statement of Holdings
| Friday, 1 July 2022 |  | 21:00 | û |  | CASCADE-RS – 4. Allocation run | During the T2S Release Weekend this process will not be executed.
| Friday, 1 July 2022 |  | 21:30 | è | Sunday, 3 July 2022, 09:30 | CASCADE - Processing of BrainTrade price differences | Payment free of delivery instruction (PFOD) for the settlement of price differences will be transmitted to T2S on Sunday, 3 July 2022, at around 09:30. They will be provided for the processing in the T2S real-time settlement (RTS) cycle.
| Friday, 1 July 2022 |  | 21:30 | ü |  | CASCADE-RS – Automated re-registration
| Friday, 1 July 2022 | 22:20 |  | è | Saturday, 2 July 2022, 18:55 | T2S – End First NTS Cycle | According to the T2S Deployment Playbook, the First NTS Cycle is expected to be completed on Saturday, 2 July 2022. The Last NTS Cycle will be started immediately afterwards.
| Friday, 1 July 2022 | 22:20 |  | è | Saturday, 2 July 2022, 18:55 | T2S – Start Last NTS Cycle
| Friday, 1 July 2022 |  | 22:30 | ü |  | Non-CCP SE trades are received from SE systems on trade date | With the introduction of the SET-GO ICSD Migration (Phase 2), "Tagesgeschäfte" are forwarded for settlement according to the custody type, that is either to Creation or T2S. Trade confirmations provided by Stock Exchanges will be queued in the CBF system until Sunday, 3 July 2022, 09:30.
| Friday, 1 July 2022 |  |  | è | Sunday, 3 July 2022, 06:30 | Pending non-CCP SE trades in custody type CSC and NCSC-T are forwarded via SETI to T2S for settlement | Based on the SET-GO Migration Approach, the transmission of "Restanten" is initiated via SETI.
| Friday, 1 July 2022 |  |  | è | Sunday, 3 July 2022, 09:30 | Newly arrived non-CCP SE trades in custody type CSC and NCSC-T are forwarded via SETI to T2S for settlement | After the implementation of the SET-GO CSD migration (Phase 2), the transmission of "Tagesgeschäfte" takes place as before after 22:30.
| Friday, 1 July 2022 |  | 22:30 | è | Sunday, 3 July 2022, 09:30 | Newly arrived non-CCP SE trades in custody type NCSC are forwarded via SETI to Creation for settlement | Since November 2021, instructions related to non-CCP SE trades in custody type NCSC are created by SETI. The timeline has been revised because of SET-GO CSD migration activities.
| Friday, 1 July 2022 |  | 22:30 | û |  | CASCADE-RS – Transfer of RS instructions to share holder register for automated re-registration | The "CASCADE-RS 4. Allocation run" is not executed and hence such details will not be available.
| Friday, 1 July 2022 |  | 23:00 | è | Sunday, 3 July 2022, starting at around 08:00 | CASCADE Reporting: MT536 – Statement of Transactions (Reporting Interval: Value in TAG 13A = 100) CBF Statement of Pending Transactions (MT537) (Reporting Interval: Value in TAG 13A = 651) MT586 – Statement of Allegements (Reporting Interval: Value in TAG 13A = 651) | The automated settlement reporting (CBF Outbound) will be queued until Sunday, 3 July 2022, 08:00. The indicated transmission time may change depending on the implementation activities. This means that reporting is transmitted after the relevant milestone has been completed. The updated MT537 message configuration applies for the first time. Therefore, not only OTC instructions, but for the first time since the SET-GO migration - depending on the client's instructions - non-CCP exchange trades can be included.
| Friday, 1 July 2022 |  |  | è | Sunday, 3 July 2022, starting after 08:00 | LION Reporting: MT537 – Statement of Pending SE Transactions (Reporting Interval: Value in TAG 13A = 200) | LION instructions that have been cancelled during the migration weekend will be reported with the cancellation reason code "LC".
| Friday, 1 July 2022 |  |  |  | 23:00 | Operational News #8 SET-GO: Receipt of daily SE trade confirmations | All trade confirmations (“Tagesgeschäfte”) will be queued and processed once the related implementation procedures have been completed. Trade confirmations in custody type: • CSC and NCSC-T will be processed as outlined in the SET-GO Migration Guide. • NCSC will continue to be processed via Creation.
|  |  |  | è | Friday, 1 July 2022, 23:00 | KADI Reporting: MT566 – Confirmation | Due to the change of the transmission time of the KADI reporting (MT564, MT568) from 19:30 to 23:00, the related confirmations (MT566) will be available on Sunday, 3 July 2022, 08:00.
| Friday, 1 July 2022 |  | 23:45 | è | Sunday, 3 July 2022, starting after 10:30 | LION Reporting for CSC and NCSC-T securities: Statement of Pending SE Transactions (MT537) (Reporting Interval: Value in TAG 13A = 250)
| Saturday, 2 July 2022 |  |  |  | 12:10 | Operational News #9 T2S: Opening of the U2A connectivity channel via ESMIG | T2(S) GUI accessible through ESMIG. For customer acting in DCP mode, an optional window to verify and / or create new routing options will be enabled until Saturday, 2 July 2022, 15:00.
| Friday, 1 July 2022 | 23:30 |  | è | Saturday, 2 July 2022, 19:45 | T2S – End Last NTS Cycle, End Night-time Settlement (NTS) | According to the T2S Deployment Playbook, the NTS processing is completed on Saturday, 2 July 2022, 19:45. After that, T2S will check if the A2A connectivity can be opened. Once the A2A connectivity opened, T2S Actors may send messages to ESMIG.
[5 empty] | Saturday, 2 July 2022, 21:10 | T2S - ESMIG (Eurosystem Single Market Infrastructure Gateway) successfully activated | Any message sent to today's existing T2S A2A channel will be lost. Messages sent to ESMIG will be queued and processed after the software deployment of T2S Release 6.0 has been completed.
| Saturday, 2 July 2022 |  |  |  | 21:45 | Operational News #10 T2S: Transmission (A2A) Settlement Messages / Reports via ESMIG | The processing of incoming instructions that reached T2S through ESMIG since Friday, 1 July 2022, 22:00, will start on Saturday, 2 July 2022, at around 17:30. T2S plans to open the A2A channel at around 21:10. The transmission of settlement results shall be provided subsequently. The Clearstream connectivity channel to T2S will be closed until Clearstream finalised the implementation activities.
| Friday, 1 July 2022 | 23:30 |  | è | Saturday, 2 July 2022, 21:50 | T2S – Start Real-time Settlement (RTS) | According to the T2S Deployment Playbook, the Real-time Processing will be executed on Saturday, 2 July 2022.
[5 empty] | Sunday, 3 July 2022, 06:00 | LION - Start LION Online | Via the CASCADE Online Functionality (HOST / PC), the transactions for LION will be re-opened. By using the function “KVLI” (display: stock exchange instructions) customers can retrieve the cancellation status of pending stock exchange instructions. Even if, the functions "KVLA" (modify / delete: stock exchange instructions) and "KVLS" (block / unblock: stock exchange instructions) are enabled, no instruction maintenance is feasible. As of Monday, instruction management for stock exchange transactions is only possible via CASCADE for custody types CSC and NCSC-T, or, since November 2021, via Creation for custody type NCSC.
| Sunday, 3 July 2022 |  |  |  | 6:00 | Operational News #11 SET-GO: Transmission of Migration Reports 1 and 2 | For SET-GO CSD Migration (Phase 2), the pending LION instructions will be cancelled at T2S and will be presented in the related customer reporting.
| Sunday, 3 July 2022 |  |  |  | 6:30 | Operational News #12 SET-GO: Go decision - Green Light start transmission to T2S | “Point of No Return” has been reached. Customers can start the deployment activities for the SET-GO CSD Migration (Phase 2).
|  |  |  | ç | Sunday, 3 July 2022, 06:30 | Opening of CBF's automated connectivity channels and CASCADE Online Functionality | The automated connectivity channels as well as the CASCADE Online functionality (HOST / PC) will be open until the maintenance window will start on Sunday, 3 July 2022, at around 11:00.
| Sunday, 3 July 2022 |  |  |  | 8:00 | Operational News #13 T2S: Start of Transmission (A2A) CBF Settlement Reporting | The CBF deployment activities for T2S Release 6.0 are completed, and settlement reporting starts.
|  |  | Saturday, 2 July 2022, 02:00 | è | Sunday, 3 July 2022, starting at 10:30 | CASCADE Reporting: MT536 – Statement of Transactions (Reporting Interval: Value in TAG 13A = 200) MT586 – Statement of Allegements (Reporting Interval: Value in TAG 13A = 801) | With this reporting interval, T2S settlement results from the First and Last NTS Cycle will be provided. In addition, settlement results provided from the RTS Cycle could be included, if T2S provided results before CBF started with the generation of the reporting interval. The reporting will be transmitted from 10:30, at the earliest, and will be completed latest before the CBF maintenance window starts.
|  |  | Saturday, 2 July 2022, 02:00 | è | Sunday, 3 July 2022, starting at 10:30 | CBF Statement of Pending OTC Transactions (MT537) (Reporting Interval: Value in TAG 13A = 801) | The updated MT537 message configuration has already been activated. Therefore, not only OTC instructions, but - depending on the client's instructions - non-CCP exchange trades can be included.
| Sunday, 3 July 2022 |  |  |  | 11:00 | Operational News #14 SET-GO: Transmission of Migration Report 3 | List of not successfully migrated trades available. It contains only SE instructions in custody type CSC or NCSC-T that have either been rejected or are being repaired by SETI as part of the migration process.
|  | 2:30 |  | è | Sunday, 3 July 2022, 10:50 | T2S – End Real-time Settlement (RTS)
|  | 2:30 |  | è | Sunday, 3 July 2022, 11:00 | T2S – Start Maintenance Window (MNTW) | After the Central Securities Depositories and the central banks agreed that the regular daily business schedule will become active, the maintenance windows will start.
|  |  | 3:00 | è | Sunday, 3 July 2022, 11:00 | CASCADE – End CASCADE Online | The CASCADE Online functionality (HOST / PC) will be available from Monday, 4 July 2022, at around 01:30.
|  |  | 3:00 | è | Sunday, 3 July 2022, 11:00 | Clearstream – Start Maintenance Window | The CBF maintenance window will be rescheduled. The maintenance activities will start once CBF completed all preceding T2S Release 6.0 activities.
|  |  | ca. 03:00 | è | Sunday, 3 July 2022, 11:00 | CBF Print Report: Lieferliste (list of pending stock exchange trades) | The reporting will be made available with the start of the CBF maintenance window.
| Sunday, 3 July 2022 |  |  |  | 11:15 | Operational News #15 T2S: Completion of Real-Time Settlement (RTS) and start of T2S and CBF maintenance windows
| Sunday, 3 July 2022 |  |  |  | 14:00 | Operational News #16 SET-GO: Start post implementation phase
| Monday, 4 July 2022 |  | 1:30 | ü |  | CASCADE – Start CASCADE Online The CBF T2S Business Day will be executed based on the regular schedule. | The CBF Online functionality (HOST / PC) will be opened for the upcoming business day.
| Monday, 4 July 2022 | 2:30 |  | ü | Sunday, 3 July 2022 21:00 | T2S – End Maintenance Window
| Monday, 4 July 2022 | 2:30 |  | ü | Sunday, 3 July 2022 21:00 | T2S – Start Real-time Settlement (RTS)
| Monday, 4 July 2022 |  | 5:00 | ü |  | CASCADE Reporting: CBF Statement of Pending Transactions (MT537) (Reporting Interval: Value in TAG 13A = 041) MT586 – Statement of Allegements (Reporting Interval: Value in TAG 13A = 041) | These messages can contain results of T2S RTS Cycle scheduled on Sunday, 3 July 2022 at around 21:00.
| Monday, 4 July 2022 |  | 5:00 | ü |  | KADI – Reporting and processing of market / reverse claims and transformation on settled underlying instructions resulting from the T2S NTS Cycle | This reporting will provide the results of the usual T2S Operational Day.
| Monday, 4 July 2022 |  | 10:00 | ü |  | LION Reporting: MT537 – Statement of Pending SE Transactions (Reporting Interval: Value in TAG 13A = 400) | The reporting to customers will be transmitted if "empty" reports are subscribed for. In a following CBF Release, the technical decommissioning is planned.
| Monday, 4 July 2022 |  | 23:00 | ü |  | LION Reporting: MT537 – Statement of Pending SE Transactions (Reporting Interval: Value in TAG 13A = 200) | LION instructions that have been cancelled during the migration weekend will be reported with the cancellation reason code "LG". With this reporting, the A2A reporting will stop for non-CCP SE trades in custody type CSC / NCSC-T.
| Tuesday, 5 July 2022 |  | 10:00 | ü |  | LION Reporting: MT537 – Statement of Pending SE Transactions | The reporting to customers will be transmitted if "empty" reports are subscribed for. In a following CBF Release, the technical decommissioning is planned.
Legend: | Revision
| ü | Processing in line with daily operational schedule
| û | Process / reporting will not be executed
| ç | Process ahead compared to daily operational schedule; see revised time
| è | Process postponed compared to daily operational schedule; see revised time
|  | Publication Operational News
Update
| i | Update: Changes are underlined and marked in color
Process completed