## EN
Date | T2S Release Schedule | CBF / T2S Business Day (CEST) | Revision | Revised Time (CEST) | Description of Event / Process of regular T2S Operational Day | CBF Comment
Monday, 14 April 2025 |  |  | i |  | CBF: Target DKK Release Weekend Schedule | Publication of the "Indicative Timeline" in preparation of the migration weekend.
Thursday, 17 April 2025 |  |  | i | 17:00 | Danmarks Nationalbank: Greenlight for DKK migration | After the end of the monetary policy day in Kronos2, the migration to Target2 begins.
Thursday, 17 April 2025 | until 18:45 |  | ü |  | CBF Business Day will be executed based on the regular schedules
Thursday, 17 April 2025 | until 18:45 |  | ü |  | T2S Operational Day will end as usual.
Thursday, 17 April 2025 | 18:45 |  | è | 23:10 | T2S – Continue with Operating Day | On T2S, the new business day will start as soon as the migration activities have been completed.
Thursday, 17 April 2025 |  | 19:00 | ü |  | CBF – Start of Day | CBF will change to value day, Tuesday, 22 April 2025, according to the regular schedule.
Thursday, 17 April 2025 |  | 19:00 | ü |  | CBF Print Report: settlement list
Thursday, 17 April 2025 |  |  | i | 19:30 | CBF: Completion end of day processing | The CBF business day 17 April 2025 is closed and the End of Day (EoD) reporting will be prepared.
Thursday, 17 April 2025 |  | 19:30 | ü |  | KADI Reporting (USA and Switzerland): MT564 – Notification MT568 – Narrative | CBF processing for corporate actions (KADI) will continue to be conducted according to the general procedures.
Thursday, 17 April 2025 |  | 19:30 | ü |  | KADI Reporting (USA and Switzerland): MT566 – Confirmations
Thursday, 17 April 2025 | 20:00 |  | è | Friday, 18 April 2025, 04:25 | T2S – Start Night-time Settlement (NTS), Start First NTS Cycle | T2 will close the transfer interface for liquidity transfers on Thursday, 17 April 2025 at around 18:45. Shortly before the Night-time Settlement, the interface will be re-opened and the liquidity transfers initiated by clients in TARGET2 will be processed so that credits to the DCAs can be executed.
Thursday, 17 April 2025 |  | 20:30 | ü |  | CASCADE Reporting: MT535 – Statement of Holdings
Thursday, 17 April 2025 |  | 21:00 | û |  | CASCADE-RS – 4. Allocation run | During the T2S Release Weekend this process will not be executed.
Thursday, 17 April 2025 |  | 21:15 | ü |  | KADI Reporting (USA and Switzerland): MT566 – Confirmations
Thursday, 17 April 2025 |  | 21:30 | ü |  | CASCADE-RS – Automated re-registration
Thursday, 17 April 2025 |  | 21:30 | ü |  | CBF Statement of Pending Transactions (MT537) (Reporting Interval: Value in TAG 13A = 651) MT586 – Statement of Allegements (Reporting Interval: Value in TAG 13A = 651)
Thursday, 17 April 2025 | 22:20 |  | è | Friday, 18 April 2025, 05:55 | T2S – Start Last NTS Cycle
Thursday, 17 April 2025 |  | 22:30 | ü |  | Non-CCP SE trades are received from SE systems on trade date as per regular processing. | Since the introduction of SET-GO, "Tagesgeschäfte" are forwarded for settlement according to the custody type, that is either to Creation or T2S.
Thursday, 17 April 2025 |  | 22:30 | ü |  | Newly arrived non-CCP SE trades in custody type CSC and NCSC-T are forwarded via SETI to T2S for settlement
Thursday, 17 April 2025 |  | 22:30 | ü |  | Newly arrived non-CCP SE trades in custody type NCSC are forwarded via SETI to Creation for settlement
Thursday, 17 April 2025 |  | 22:30 | û |  | CASCADE-RS – Transfer of RS instructions to share holder register for automated re-registration | The "CASCADE-RS 4. Allocation run" is not executed and hence such details will not be available.
Thursday, 17 April 2025 |  | 23:00 | è | Friday, 18 April 2025, starting 12:30 | KADI Reporting (USA and Switzerland): MT564 – Notification MT568 – Narrative | Due to the late Start of Day procedure in T2S, the KADI reports will be delivered on Friday, 18 April 2025, 12:30.
Thursday, 17 April 2025 |  | 23:00 | è | Friday, 18 April 2025, starting 12:30 | KADI Reporting: MT566 – Confirmation | Due to the late Start of Day procedure in T2S, the KADI confirmations will be delivered on Friday, 18 April 2025, 12:30.
Thursday, 17 April 2025 |  | 23:00 | è | Friday, 18 April 2025, starting 12:30 | CASCADE Reporting: MT536 – Statement of Transactions (Reporting Interval: Value in TAG 13A = 220) | Due to the late Start of Day procedure in T2S, the reports will be delivered on Friday, 18 April 2025, 12:30.
Thursday, 17 April 2025 | 23:30 |  | è | Friday, 18 April 2025, 06:05 | T2S – End Last NTS Cycle, End Night-time Settlement (NTS) | According to T2S, the NTS processing is completed on Friday, 18 April 2025, 06:05.
Thursday, 17 April 2025 | 23:30 |  | è | Friday, 18 April 2025, 06:05 | T2S – Start Real-time Settlement (RTS) | According to T2S, the Real-time Processing will be executed on Friday, 18 April 2025, 06:05.
Friday, 18 April 2025 |  | Friday, 18 April 2025, 02:00 | è | Friday, 18 April 2025, starting at 13:30 | CASCADE Reporting: MT536 – Statement of Transactions (Reporting Interval: Value in TAG 13A = 200) CBF Statement of Pending Transactions (MT537) (Reporting Interval: Value in TAG 13A = 801) MT586 – Statement of Allegements (Reporting Interval: Value in TAG 13A = 801) | The automated settlement reporting (CBF Outbound) will be queued until Friday, 18 April 2025, 12:30. The indicated transmission time may change depending on the migration activities. This means that reporting is transmitted after the relevant milestone has been completed.
Friday, 18 April 2025 | 2:30 |  | è | Sunday, 20 April 2025, 08:00 | T2S – End Real-time Settlement (RTS)
Friday, 18 April 2025 | 2:30 |  | è | Sunday, 20 April 2025, 08:00 | T2S – Start Maintenance Window (MNTW) | After the Central Securities Depositories and the central banks agreed that the daily business schedule will continue to be followed, the maintenance window will start.
Friday, 18 April 2025 |  | Friday, 18 April 2025, 03:00 | è | Friday, 18 April 2025, 15:00 | Clearstream – Start Maintenance Window | The CBF maintenance window will be rescheduled. The maintenance activities will start once CBF completed all preceding activities.
Saturday, 19 April 2025 |  | 17:00 | ü |  | Closing of the 1CAS message flow: MT564 – Notification MT566 - Confimation MT568 – Narrative | The Custody message flow will be closed as on usual weekends. Reopening is planned for Sunday, 20 April 2025, 21:00. No release schedule will be applied.
Sunday, 20 April 2025 |  | 21:00 | ü |  | Re-opening of the Custody message flow: MT564 – Notification MT566 - Confimation MT568 – Narrative
Tuesday, 22 April 2025 |  | 1:30 | ü |  | CASCADE – Start CASCADE Online The CBF T2S Business Day will be executed based on the regular schedule. | The CBF Online functionality will be opened for the upcoming business day.
Tuesday, 22 April 2025 | 2:30 |  | ü |  | T2S – End Maintenance Window
Tuesday, 22 April 2025 | 2:30 |  | ü |  | T2S – Start Real-time Settlement (RTS)
Tuesday, 22 April 2025 |  | 5:00 | ü |  | CASCADE Reporting: CBF Statement of Pending Transactions (MT5317) (Reporting Interval: Value in TAG 13A = 041) MT586 – Statement of Allegements (Reporting Interval: Value in TAG 13A = 041) | These messages can contain results of T2S RTS Cycle scheduled on Friday, 18 April 2025 at around 06:05.
Tuesday, 22 April 2025 |  | 5:00 | ü |  | KADI – Reporting and processing of market / reverse claims and transformations on settled underlying instructions resulting from the T2S NTS Cycle. | This reporting will provide the results of the usual T2S Operational Day.
Legend:
Revision
ü | Processing in line with daily operational schedule
û | Process / reporting will not be executed
ç | Process ahead compared to daily operational schedule; see revised time
è | Process postponed compared to daily operational schedule; see revised time
i | information only for migration weekend; no corresponding process in the daily operational schedule